# CAUTI / VAP / UE Research and Deliverables Plan

Prepared: February 26, 2026
Scope: SICU quality deliverables for committee execution and PI tracking

## Program Goal

Create a single practical workplan that converts current discussions into measurable CAUTI, VAP, and UE improvements over 90 days.

## Deliverables by Workstream

## 1) CAUTI Workstream

### Deliverables

- Final trauma/SICU Foley guideline (committee-approved version).

- One-page resident/APP bedside quick guide.

- Urine-culture stewardship trigger card for rounds.

- CAUTI national benchmark and CMS impact brief for leadership alignment.

- Monthly CAUTI process dashboard:

- Foley device utilization

- Foley-days with documented indication

- Non-indicated urine cultures

- CAUTI events/SIR

### Data Sources

- EMR order and documentation fields

- Infection prevention event log

- Unit audit sampling

## 2) VAP Workstream

### Deliverables

- RN/RT oral-care accountability standard (who does what, when).

- Subglottic ET rollout implementation tracker.

- SAT/SBT compliance tracker (time-start and completion reason).

- Monthly VAP/vent-day dashboard with baseline and trend.

### Data Sources

- RT logs and vent-day counts

- EMR task completion data

- Quality reporting extracts

## 3) UE Workstream

### Deliverables

- One-page UE event form (RN + RT + provider completion in 1 hour).

- UE event tracker (rate per 100 ventilator days).

- Post-event huddle checklist.

- Monthly UE review section in SICU PI meeting template.

### Data Sources

- Bedside UE forms

- RT ventilator day denominator

- PI committee logs

## 4) Case Review Standardization

### Deliverables

- Case-closure template language for SICU minutes.

- Event-classification checklist (CAUTI/HAP/VAP/other) to reduce mislabeling.

- Required-elements checklist for self-extubation documentation.

## 30-60-90 Day Timeline

| Window | Dates | Priority Outputs |
| --- | --- | --- |
| 0-30 days | 2026-02-26 to 2026-03-27 | Finalize templates (Foley quick guide, UE event form, closure language); start baseline dashboards |
| 31-60 days | 2026-03-28 to 2026-04-26 | Launch active audits (CAUTI culture triggers, oral care compliance, SAT/SBT timing); first full monthly report |
| 61-90 days | 2026-04-27 to 2026-05-26 | Run first performance review cycle; adjust thresholds/workflows; publish phase-2 recommendations |

## Owner Matrix (Assign Named Person at Next Meeting)

| Deliverable Group | Default Owner Role | Backup Role |
| --- | --- | --- |
| CAUTI guideline + stewardship tools | SICU Director / APP Lead | Infection Prevention |
| VAP oral-care + vent process tracker | RT Lead + ICU Nursing Lead | Quality Analyst |
| UE form/tracker/huddle | SICU Director + ICU Charge RN | RT Lead |
| Dashboards and monthly reporting | Quality Lead | Informatics |

## Success Metrics (Initial Targets)

- =90% Foley-days with documented indication.

- =30% reduction in non-indicated urine cultures.

- =85% documented oral-care interval compliance.

- =85% SAT/SBT documentation compliance before 08:00.

- UE events tracked at 100% capture with documented post-event huddle.

## Meeting Cadence for This Plan

- Weekly 15-minute operational huddle (execution blockers only).

- Monthly SICU committee review (metrics + decisions).

- Quarterly PI summary (trend, outcomes, resource requests).